Final Elundini Local Municipality SCM Policy for Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM)

July 2026

Elundini Local Municipality SCM Policy for Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM)

for use by Elundini Local Municipality that is subject to the Local Government Municipal Finance Management Act, of 2003 (Act 56 of 2003) (MFMA)

Preface

This policy was adopted by the Elundini Municipality Council in terms of the Model SCM Policy for Infrastructure Delivery Management which is attached to MFMA Circular 77 has been issued in terms of Section 168 of the Municipal Finance Management Act of 2003 (Act 56 of 2003) (MFMA) in support of Regulation 3(2),( c ) of the MFMA Supply Chain Management Regulations as a Treasury guideline determining a standard for municipal supply chain management policies.

Council Resolution for this Policy is ___________________ and was approved by the Council on the _____________________

The National Treasury, in consultation with relevant stakeholders, initiated the SIPDM review process which resulted in the development of the Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM). The LGFIDPM introduces minimum requirements for effective governance of infrastructure delivery and procurement management.

This policy seek to replace the Standard for Infrastructure Procurement and Delivery Management (SIPDM) was issued for municipalities and communicated in MFMA Circular No 77 of 2015/2016 , this circular intended to provide guidance to municipalities and municipal entities on the establishment of a suitable supply chain management system for infrastructure delivery which is better able to deliver value for money, while minimizing the scope for fruitless and wasteful expenditure. The Model SCM Policy for Infrastructure Delivery Management Circular No 77 of 2015/2016 has now been replaced by MFMA Circular No 106.

The LGFIDPM provides minimum requirements for the implementation of Infrastructure Delivery and Procurement Management through the:

- Project processes for infrastructure delivery management, and

- Infrastructure procurement gates.

The Framework specifies the allocation of responsibilities for performing activities and making decisions at project stages and procurement gates.

The Model Supply Chain Management (SCM) Policy for Infrastructure Procurement and Delivery Management which is attached to MFMA Circular 106 has also aligned to regulation 2(1), (c),(e), and regulation 3(1) as set out below that was issued in terms of Section 168 of the Municipal Finance Management Act of 2003 (Act 56 of 2003) (MFMA).

- Regulation 2(1) of the Municipal SCM Regulations provides that each municipality and each municipal entity must in terms of section 111 of the Act have and implement a supply chain management policy that amongst others: –

(c ) complies with –

(ii)	any minimum norms and standards that may be prescribed in terms of section 168 of the Act; and

(e) does not undermine the objective for uniformity in supply chain management systems between organs of state in all spheres;

- Regulation 3(1) of the Municipal Supply Chain Management Regulations requires the accounting officer of a municipality or municipal entity to, amongst others, at least annually review the implementation of the SCM Policy and, if necessary, submit proposals for the amendment of the policy to the council or the board of directors.

- Regulation 3(2) then goes further by stating that the accounting officer may for purpose of regulation 3(1) make use of any Treasury guidelines determining standards for municipal supply chain management policies in drafting their SCM policies.

- Regulation 3(2)(c) furthermore requires that any deviation from the guideline standard be reported to the National Treasury and the relevant provincial treasury.

This document establishes the minimum requirements for Elundini Local Municipality as its organisational policy for Infrastructure Procurement and Delivery Management, namely:

- assign responsibilities for approving or accepting deliverables associated with a gate in the control framework or authorising a tender process;

- establish committees which are required by law or equivalent quality management and governance arrangements; and

- establish delegations for the awarding of a contract or the issuing of an order

This Model Supply Chain Management (SCM) Policy for Infrastructure Procurement and Delivery Management of Elundini Local Municipality is aligned with the Supply Chain Management Regulations issued in terms of the Local Government: Municipal Finance Management Act of 2003.

There are unavoidably duplications in supply chain management policies for general goods and services and those for infrastructure delivery management arising from not only regulatory requirements but also an overlap in support functions such as the receipt of bids and advertising of bids. This model policy document is accordingly issued as a supplementary (Annexure A), to the Elundini Local Municipality’s master policy for supply chain management system, for general goods and services.

The approach to procurement documentation is significantly different between general goods and services and infrastructure delivery. Documents for general goods and services, are based on the National Treasury General Conditions of Contract (GCC) which focuses on the rights and obligations of the parties in a generic manner and also deals with aspects of the bidding processes.

This GCC requires that goods conform to the standards mentioned in the bidding documents and specifications and is used with standard bidding documents which include an invitation to bid, price schedules, local content, certificate of bid independence, declaration of bidders past SCM practices, etc. Accordingly, the major variables between documents are the specifications or terms of reference and the evaluation criteria which ensures that bids are awarded on the basis of the lowest price for meeting a minimum standard. Contracts or service level agreements are frequently negotiated after the award of the bid.

In contrast, infrastructure procurement documents are based on a standard approach to the formatting and compilation of procurement documents used in conjunction with flexible standard conditions for the calling for an expression of interest and conditions of tender and a standard form of contract selected from a prescribed list. These standard forms of contract permit different allocations of risk to the parties to a contract and a wide range of pricing strategies to be pursued.

This approach to procurement documentation enables procurement strategy and tactics to be exercised both in the awarding and in the performance of a contract in order to realise best value for money outcomes. Very seldom are material changes made in the draft contract which is issued to tenderers during the process of offer and acceptance as the offer is based on the selected allocation of risks and pricing strategies.

There are accordingly significant differences in the approach to bid specification and bid evaluation committees between the SCM system for general goods and services and that for infrastructure as a very different skills sets coupled with contextual knowledge is required. On the other hand, the bid adjudication committee is a governance committee which can deal with submissions emanating from both supply chains policies.

The Supply Chain Management Regulations issued in terms of the MFMA permit the accounting officer herein after referred to as Municipal Manager to make use of any Treasury guidelines determining standards for municipal supply chain management policies and to submit to the council of Elundini Local Municipality a guideline standard known as the Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM) attached as (Annexure B).

The Regulations furthermore require the Municipal Manager of Elundini Local Municipality shall report any deviation from the guideline standard to the National Treasury and the relevant Provincial Treasury. Accordingly, all departures from this model policy and the Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM), which is embedded within the policy, will be reported to the relevant treasury.

Elundini Local Municipality’s SCM Policy for Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM)

Contents

1	Scope	1

2	Terms, definitions and abbreviations	1

2.1	Terms and definitions	1

2.2	Abbreviations	2

3	General requirements	2

3.1	Delegations	2

1.2	Implementation of the Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM)	3

3.3	Policy Intent and purpose	3

3.3.1	General	3

3.3.3	Framework For Infrastructure Procurement	4

4	Minimum Requirement for Infrastructure Procurement.	4

5	Infrastructure Procurement Gates	5

6	The Infrastructure Delivery Management Project Processes	1

7	Gateway Reviews	5

Gateway reviews for mega capital projects	5

Establishment and composition  of gateway review team	5

Terms of reference for the gateway team	5

8	Supervision of this Infrastructure Procurement and Delivery Policy	6

8.1.1.Objections and complaints	6

8..1.1.1 Objections and complaints are dealt with in section 102 of the Master SCM policy	6

8.1.2 Resolution of disputes, objections, complaints and queries	6

9	Control framework for infrastructure delivery management	7

9.1 Assignment of responsibilities for approving or accepting end of stage deliverables	7

9.2 	Additional requirements	7

10	Committee system for procurement	7

# Scope

This policy establishes the Elundini Local Municipality’s policy for infrastructure procurement and delivery management in accordance with the provisions of the regulatory frameworks for procurement and supply chain management. It includes the procurement of goods and services necessary for a new facility to be occupied and used as a functional entity but excludes:

- the storage of goods and equipment following their delivery to Elundini municipality which are stored and issued to contractors or to employees;

- the disposal or letting of land;

- the conclusion of any form of land availability agreement;

- the leasing or rental of moveable assets; and

- Public private partnerships.

The Framework provides minimum requirements for the implementation of Infrastructure Delivery and Procurement Management through the:

- Project processes for infrastructure delivery management, and

- Infrastructure procurement gates.

The Framework specifies the allocation of responsibilities for performing activities and making decisions at project stages and procurement gates.

# Terms, definitions and abbreviations

## 2.1	Terms and definitions as defined in the Local Government Framework for Infrastructure Delivery and Procurement Management.

For the purposes of this document, the definitions and terms given in the standard and the following apply:

Approved: Officially agreed and signed-off by an Accounting Officer or a delegated person / body.

Construction: Everything constructed or resulting from construction operations.

Employer: Organ of state intending to, or entering into, a contract with a contractor.

Gate: A control point at the end of a process where a decision is required before proceeding  to the next process or activity.

Gateway review: An independent review of the available information at a gate upon which a decision is made whether to proceed to the next process, or not.

Infrastructure:  a) Immovable asset, which is acquired, constructed or results from construction operations; or b) Movable asset, which cannot function independently from purpose-built immoveable asset(s).

Infrastructure delivery: The combination of all planning, technical, administrative and managerial actions associated with the construction, supply, refurbishment, rehabilitation, alteration, maintenance, operation or disposal of infrastructure.

Infrastructure procurement: The procurement of goods or services, including any combination thereof, associated with the acquisition, refurbishment, rehabilitation, alteration, maintenance, operation or disposal of infrastructure.

Organ of State: Any department of state or administration in the national, provincial and local sphere of government.

Procurement strategy: The selected packaging, contracting, pricing and targeting strategy and procurement procedure for a particular procurement.

Project: A unique set of processes consisting of coordinated and controlled activities with start and end dates, performed to achieve the project objective.

Stage: A collection of periodical and logically related activities in the Project Management Control Stages, that culminates in the completion of an end of stage deliverable.

Other : As approved in this Policy by the Elundini Municipality Council

Mega Capital Projects : Projects that amount to R50 Million and above.

A Framework agreement is defined in SANS ISO 10845 as “an agreement between an employer and one or more contractors, the purpose of which is to establish the terms governing orders to be awarded during a given period, in particular with regard to price and, where appropriate, the quantity envisaged.”

## 2.2	Abbreviations

For the purposes of this document, the following abbreviations apply

CIDB:      Construction Industry Development Board

IDP:         Integrated Development Plan

FIDPM:    Framework for Infrastructure Delivery and Procurement Management

MFMA:     Municipal Finance Management Act

PSP:        Professional Service Provider

PPPFA:    Preferential Procurement Policy Framework Act

SCM:       Supply Chain Management

SDBIP:    Service Delivery Budget Implementation Plan

# General requirements

## 3.1	Delegations

    - The council of Elundini Local Municipality hereby delegates all powers and duties to the municipal manager which are necessary to enable the municipal manager to:

a)	discharge the supply chain management responsibilities conferred on accounting officers in terms of Chapter 8 or 10 of the Local Government Municipal Finance Management Act of 2003 and this document;

b)	maximise administrative and operational efficiency in the implementation of this document;

c)	enforce reasonable cost-effective measures for the prevention of fraud, corruption, favouritism and unfair and irregular practices in the implementation of this document; and

d)	comply with his or her responsibilities in terms of section 115 and other applicable provisions of the Local Government Municipal Finance Management Act of 2003 Act.

    - No amendment shall be made from the provisions of this policy without the approval of the Council.

    - The municipal manager shall for oversight purposes:

a)	within 30 days of the end of each financial year, submit a report on the implementation of this the policy and the equivalent policy of any municipal entity under the sole or shared control of the Elundini Local Municipality, to the council of the Elundini Local Municipality.

b)	whenever there are serious and material problems in the implementation of this policy, immediately submit a report to the council;

- within 10 days of the end of each quarter, submit a report on the implementation of the policy to the mayor ; and

- make the reports public in accordance with section 21A of the Municipal Systems Act of 2000.

## Implementation of the Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM)

3.2.1	Framework for Infrastructure procurement and delivery management will be undertaken in accordance with all applicable legislation and the relevant requirements of the latest edition of the (LGFIDPM)

3.2.2	No departures shall be made from the provisions of the National Treasury Framework for Infrastructure Procurement and Delivery Management without the approval of the Accounting Officer

## 3.3	Policy Intent and purpose

### 3.3.1	General

3.3.1.1	The policy intent of the Elundini Local Municipality SCM Policy for Local Government Framework for Infrastructure Delivery and Procurement Management (LGFIDPM) is to facilitate the achievement of sustainable, uniform and consistent approach in the infrastructure procurement and delivery management by Elundini Local Municipality and entities. In this context, sustainability implies a commitment to long-term planning and budgeting; the development of outcomes that consider asset management principles; environmental and socio-economic impacts.

3.3.1.2	This SCM Policy for Infrastructure Procurement and Delivery Management has been developed with the objective of:

- ensuring that the Elundini Local Municipality assigned with the responsibility (in terms of relevant legislation) to deliver infrastructure or those appointed to act as the implementing agents for infrastructure delivery comply with The National Treasury Instruction Circular 106

- addressing the National Treasury LGFIDPM need to establish and implement a framework to:

  - assign responsibilities for approving or accepting deliverables associated with a gate in the control framework or authorising a tender process;

  - establish committees which are required by law;

  - establish delegations for the awarding of a contract or the issuing of an order; and

  - establish ethical standards for those involved in the procurement and delivery of infrastructure;

- assigning the centrally led infrastructure delivery implementing agency (IA) status to the relevant municipal entity and mechanism for assigning sub-IA’s or delivery agents in cases where Elundini Local Municipality does not have capacity to deliver the implementing agency mandate; and

- providing a framework for implementing the whole of Elundini Local Municipality’s local economic development strategy priorities through infrastructure procurement and delivery management.

### 3.3.3	Framework For Infrastructure Procurement

3.3.2.1	 The framework for infrastructure procurement outlines the minimum infrastructure procurement policy requirements for municipal planning and implementation. The strategic direction set in the Integrated Development Plan (IDP) informs the framework for infrastructure procurement. For example, procurement strategies must be aligned to the municipality’s developmental and internal transformation needs, as specified in the IDP.

# Minimum Requirement for Infrastructure Procurement.

      - Infrastructure procurement must be undertaken in accordance with all applicable Infrastructure Procurement related legislation and this Framework.

      - Infrastructure procurement must be implemented in accordance with the institutional Supply Chain.

      - Management System, which promotes differentiated procurement for infrastructure.

      - Infrastructure procurement must be implemented in accordance with the procurement gates prescribed in clause 4.2.2.2 below.

      - The Accounting Officer must ensure that a budget is available for the duration of the project, in line with MFMA provisions for capital and operating budgets.

      - The Accounting Officer must ensure that cash flow management processes are in place to meet payment obligations within the time periods specified in the contract.

      - Procurement gates provided in 4.2.2.2 below must be used, as appropriate, to:

- Authorise commencement of activities that lead to the next control gate;

- Confirm conformity with requirements; and/or

- Provide information to eliminate any cause of non-conformity and to prevent reoccurrence.

      - The authorisation to proceed to the next procurement gate must be given by a delegated person or body. The delegated person or body must be able to apply relevant built environment knowledge and skill to achieve the intended results required at the relevant procurement gate. The level of detail contained in the documentation on which a decision to proceed to the next procurement gate is made, must be sufficient to enable an informed decision.

      - The Accounting Officer must develop and implement effective and efficient emergency procurement procedures, including relevant approval delegation, in compliance with relevant legislation.

      - The Accounting Officer must develop and implement an effective and efficient infrastructure disposal policy in line with the Municipal Asset Transfer Regulations. The institution may consider disposal strategies aligned to their internal disposal policy, prior to proceeding with the procurement strategy.

      - The Accounting Officer must keep records of Procurement Gate Approvals, in a manual or electronic format, with the following minimum requirements:

- Procurement gate;

- Delegated person/s or body;

- Date on which the approval request was received;

- Date on which the approval was actioned; and

- Signature of the delegated person or body.

      - All assets must be recorded in the municipal asset register as required by the GRAP standards.

# Infrastructure Procurement Gates

      - Procurement Gate 1 (PG 1)

- Initiate a procurement process;

- Minimum Requirement for PG 1:

- Establish and clarify the procurement need, aligned to the municipality’s development and transformation priorities specified in the IDP.

- Determine a suitable title for the procurement, to be applied as the project description.

- Prepare the broad scope of work for the procurement.

- Perform market analysis.

- Estimate the financial value of proposed procurement and contract for budgetary purposes, based on the broad scope of work.

- Confirm the budget.

- Compliance with section 33 of the MFMA with respect to community and stakeholder consultation.

- PG 1 is complete when a designated person or body makes the decision to proceed/not to proceed, with the procurement of the infrastructure.

      - Procurement Gate 2 (PG 2)

- Approve procurement strategy to be adopted.

- Minimum Requirement for PG 2:

- Develop a procurement strategy aligned to the institutional procurement strategy:

Establish contracting and pricing strategy comprising of an appropriate allocation of responsibilities and risks; and the methodology for contractor payments.

- Identify service required for works.

- Decide on contracting strategy.

- Decide on pricing strategy.

- Decide on form of contract.

- Establish opportunities for promoting preferential procurement in compliance with legislative provisions and the Construction Sector Code.

c) PG 2 is complete when a delegated person or body approves the procurement strategy that is to be adopted.

      - Procurement Gate 3 (PG 3)

- Approve procurement documents.

- Minimum requirements for PG 3:

- Prepare procurement documents that are compatible with:

- approved procurement strategies.

- project management design documentation.

- PG 3 is complete when the Bid Specification Committee approves the procurement document.

      - Procurement Gate 4 (PG 4)

- Confirm that cash flow processes are in place to meet projected contractual obligations.

- Minimum requirement for PG 4

- Confirm that cash flow processes are in place to meet contractual obligations.

- Establish control measures for settlement of payments within the time period specified in the contract.

c) PG 4 is complete when a delegated person or body confirms in writing that cash flow processes are in place; and control measures are established for the procurement to take place.

      - Procurement Gate 5 (PG5)

- Solicit tender offers.

- Minimum requirements for PG 5

- Invite contractors to submit tender offers.

- Receive tender offers.

- Record tender offers.

- Safeguard tender offers.

- PG 5 is complete when tender offers received are recorded and safeguarded by a delegated person from the SCM unit.

      - Procurement Gate 6 (PG6)

- Evaluate tender offers premised on undertakings and parameters established in procurement documents.

- Minimum Requirement for PG 6:

- Determine whether tender offers are complete.

- Determine whether tender offers are responsive.

- Evaluate tender submissions.

- Review minimum compliance requirements for each tender.

- Perform a risk analysis.

- Prepare a report on tender offers received, and on their achievement of minimum compliance.

- PG 6 is complete when the chairperson of the Bid Evaluation Committee approves the BEC report

      - Procurement Gate 7 (PG 7)

- Award the contract.

- Minimum Requirement for PG 7:

- Bid adjudication committee review of the BEC evaluation report.

- Bid Adjudication Committee makes an award.

- Accounting Officer approval of the tender process.

- Notify successful tenderer and unsuccessful tenderers of the outcome.

- Sign contract document.

- Formally accept tender offer.

- PG 7 is complete when the Accounting Officer, or the Bid Adjudication Committee where delegated, confirms that the tenderer has provided evidence of complying with all requirements stated in the tender data and formally accepts the tender offer in writing, and issues the contractor with a signed copy of the contract.

      - Procurement Gate 8 (PG 8)

- Administer and monitor the contract.

- Minimum Requirements for PG 8:

- Finance department to:

- Capture contract award data.

- Manage cash flow projection.

- Administer contract in accordance with the terms and provisions of the contract.

- Delivery department to:

- Ensure compliance with contractual requirements.

- PG 8 is complete when a delegated person captures the contract completion/termination data (close out reports and relevant documents), including payment certificates due.

| Activity |  | Sub-Activity (see Table 3 of the standard) |  | Key action | Person assigned responsibility to perform key action |
| --- | --- | --- | --- | --- | --- |
| 1* | Initiate a procurement process; | PG1 | Obtain permission to start with the procurement process | - Establish and clarify the procurement need, aligned to the municipality’s development and transformation priorities specified in the IDP. - Determine a suitable title for the procurement, to be applied as the project description. - Prepare the broad scope of work for the procurement. - Perform market analysis. - Estimate the financial value of proposed procurement and contract for budgetary purposes, based on the broad scope of work. - Confirm the budget. - Compliance with section 33 of the MFMA with respect to community and stakeholder consultation. | End user and IPD Unit, CFO |
|  | PG 1 is complete when a designated person or body makes the decision to proceed/not to proceed, with the procurement of the infrastructure. |  |  |  |  |
| 2* | Decide on procurement strategy | PG2 | Obtain approval for procurement strategies that are to be adopted . | Develop a procurement strategy aligned to the institutional procurement strategy: Establish contracting and pricing strategy comprising of an appropriate allocation of responsibilities and risks; and the methodology for contractor payments. a) Identify service required for works. b) Decide on contracting strategy. c) Decide on pricing strategy. d) Decide on form of contract. e) Establish opportunities for promoting preferential procurement in compliance with legislative provisions and the Construction Sector Code. | Accounting Officer, in consultation, for User Department and IPD, Unit. |
|  | PG 2 is complete when a delegated person or body approves the procurement strategy that is to be adopted. |  |  |  |  |
| 3 | Approve procurement documents. | PG3 | Obtain approval for procurement documents | Prepare procurement documents that are compatible with: a) approved procurement strategies. b) project management design documentation | Chair of the Specification Committee who accept procurement documentation and submit to the Accounting Officer who approves and endorses the procurement documentation. |
|  | PG 3 is complete when the Bid Specification Committee approves the procurement document |  |  |  |  |
| 4 | Confirm that cash flow processes are in place to meet projected contractual obligations. | PG 4 | Confirm that cash flow processes are in place to meet projected contractual obligations | Confirm that cash flow processes are in place to meet contractual obligations. Establish control measures for settlement of payments within the time period specified in the contract. | Director I P& D |
|  | PG 4 is complete when a delegated person or body confirms in writing that cash flow processes are in place; and control measures are established for the procurement to take place. |  |  |  |  |
| 5 | Solicit Tender Offers | PG 5 | Invitation of tender offers | 1) Invite contractors to submit tender offers. 2) Receive tender offers. 3) Record tender offers. 4) Safeguard tender offers. | Supply Chain Management |
|  | PG 5 is complete when tender offers received are recorded and safeguarded by a delegated person from the SCM unit. |  |  |  |  |
| 6 | Evaluate tender offers | PG 6 | Evaluate tender offers premised on undertakings and parameters established in procurement documents. | 1) Determine whether tender offers are complete. 2) Determine whether tender offers are responsive. 3) Evaluate tender submissions. 4) Review minimum compliance requirements for each tender. 5) Perform a risk analysis. 6) Prepare a report on tender offers received, and on their achievement of minimum compliance | The appointed Chair of Evaluation Committee who accept evaluation report submit recommendations to Adjudication Committee. Accounting Officer approves/endorse or refer back, the resolution taken by the Adjudication Committee PG 6 is complete when the chairperson of the Bid Evaluation Committee approves the BEC report |
|  | PG 6 is complete when the chairperson of the Bid Evaluation Committee approves the BEC report. |  |  |  |  |
| 7 | Award contract | PG7 | Confirm recommendations contained in the tender evaluation report Award contract | Review recommendations of the evaluation committee and refer back to evaluation committee for reconsideration or make recommendation for award Bid adjudication committee review of the BEC evaluation report. Bid Adjudication Committee makes an award. Accounting Officer approval of the tender process. Notify successful tenderer and unsuccessful tenderers of the outcome. Sign contract document. Formally accept the tender offer in writing and issue the contractor with a signed copy of the contract | PG 7 is complete when the Accounting Officer, the Bid Adjudication Committee where delegated, confirms that the tenderer has provided evidence of complying with all requirements stated in the tender data and formally accepts the tender offer in writing, SCM issues the contractor with a signed copy of the contract |
|  |  | PG 7 is complete when the Accounting Officer, or the Bid Adjudication Committee where delegated, confirms that the tenderer has provided evidence of complying with all requirements stated in the tender data and formally accepts the tender offer in writing, and issues the contractor with a signed copy of the contract. |  |  |  |
| 8 | Administer and monitor the contract. | PG8 | Ensure compliance with contractual requirements. Upload data in financial management and payment system | - Administer and monitor the contract. - Finance department to: - Capture contract award data. - Manage cash flow projection. - Administer contract in accordance with the terms and provisions of the contract. - Delivery department to: (i) Ensure compliance with contractual requirements. | SCM , IP&D |
|  |  | PG 8 is complete when a delegated person captures the contract completion/termination data (close out reports and relevant documents), including payment certificates due |  |  |  |

Table 1: Procurement activities and gates associated with the formation and conclusion of contracts.

# The Infrastructure Delivery Management Project Processes

- The project process of infrastructure delivery management contains control stage deliverables at the end of each stage. Table 1 outlines the stage deliverables that must be approved. The control stages are specific to project management processes; and outline and describe the stages in the life of a project from start to end. The specific stages are determined by the specific project’s governance and control needs. The stages follow a logical sequence with a specified start and end. The deliverable is considered to have passed through the relevant stage when it is approved and signed off. The project then moves on to the next sequential stage. The municipality’s organisation shall reflects an engagement between the Budget Treasury Office, Engineers and Planners when developing and approving projects. It is also expected that there should be engagements with the National and Provincial Treasury where appropriate or where projects dictate so.

- Procurement of PSPs and Contractors can occur at different points in the project stages.

- Additional stages may be added to the described stages above, if deemed necessary. For example, additional stages could include those necessary to ensure that project activities are appropriately carried out and stages linked. Contract activities would, in many instances, be contingent upon the requirements of the specific contract being used.

- For project progress using the project stages, reporting must be for the deliverable achieved in the stage immediately prior to the ‘in progress’ stage. For example, if a project is shown as being at Stage No. 3 (Design Development), it implies that the deliverable for Stage No. 2 (i.e. the Concept Report) has been achieved; and that the deliverable for Stage 3 (i.e. the Design Development Report) is in the process of being prepared.

- Where the municipality engages another organ of state to provide agency services, a service delivery agreement must be developed that outlines the roles and responsibilities for each organ of state; and establishes a relationship between the client and the implementer. The development of all deliverables should be carried out in a cooperative and consultative manner between the Client and Implementer parties. All deliverables must be developed and signed off in compliance with the specific service delivery agreement.

| Stage |  | Person assigned the responsibility for approving or accepting end of stage deliverables |  |
| --- | --- | --- | --- |
| No | Name |  |  |
| 0 | Project initiation | User Department will initiate and Project Management Unit accepts the initiation report from the User Department. after consultation with Infrastructure Planning Development Unit and Strategic User Department. Initiation Report or Pre-feasibility Report (i) The Initiation Report defines project objectives, needs, acceptance criteria, organisation’s priorities and aspirations, and procurement strategies, which set out the basis for the development of the Concept Report. Or (ii) A Pre-feasibility Report is required on Mega Capital Projects, to determine whether to proceed to the Feasibility Stage; where sufficient information is presented to enable a final project implementation decision to be made. Mega capital projects should be determined in the municipality’s policy approved by the Municipal Council. Stage 1 is complete when the Initiation Report or Pre-feasibility Report is approved. |  |
| 2 | Concept | Project management Unit accept and recommended by Infrastructure Planning and development Directorate in consultation with end user department, for MM recommendation and approval by municipal manager The feasibility report on mega projects as identified in this standard, Projects R50 Million and above submit to Council for Information, providing it was approved on IDP. Municipal manager approve/not approved or refer back the feasibility report based on recommendation by the Director Infrastructure Planning and development, after consultation with end User Department, Municipal Finance and the, Strategic User Department. Municipal manager, If required refer back to council if deviate from IDP, and or report of outcome. Concept Report or Feasibility Report (i) The Concept Stage presents an opportunity for the development of different design concepts to satisfy the project requirements developed in Stage 1. This stage presents alternative approaches and an opportunity to select a particular conceptual approach. The objective of this stage is to determine whether it is viable to proceed with the project, premised on available budget, technical solutions, time frame and other information that may be required. (ii) The Concept Report should provide the following minimum information: a) Document the initial design criteria, cost plan, design options and the selection of the preferred design option; or the methods and procedures required to maintain the condition of infrastructure, or the project. b) Establish the detailed brief, scope, scale, form and cost plan for the project, including, where necessary, the obtaining of site studies and construction and specialist advice. c) Provide an indicative schedule for documentation and construction, or maintenance services, associated with the project. d) Include a site development plan, or other suitable schematic layouts, of the works. e) Describe the statutory permissions, funding approvals and utility approvals required to proceed with the works associated with the project. f) Include a baseline risk assessment for the project and a health and safety plan, which is a requirement of the Construction Regulations issued in terms of the Occupational Health and Safety Act. g) Contain a risk report, need for further surveys, tests, investigations, consents and approvals, if any, during subsequent stages. (iii) A Feasibility Report must provide the following minimum information: a) Details regarding the preparatory work covering: - A needs and demand analysis with output specifications. - An options analysis. b) A viability evaluation covering: - A financial analysis. - An economic analysis, if necessary. c) A risk assessment and sensitivity analysis; d) A professional analysis covering: - A technology options assessment. - An environmental impact assessment. - A regulatory due diligence. e) An implementation readiness assessment covering: - Institutional capacity. - A procurement plan. Stage 2 is complete when the Concept Report or the Feasibility Report is approved. |  |
|  | Concept and viability | Project Management Unit accept and recommended by Infrastructure Planning and development Directorate in consultation with end user department, for MM recommendation and approval by Municipal manager Municipal manager approve/not approved or refer back the Concept and viability report based on recommendation by the Director Infrastructure Planning and development, after consultation with end User Department, Municipal Finance and the, Strategic User Department. Municipal Manager, If required refer back to council if deviate from IDP, and or report of outcome |  |
| 3 | Design development Report | Project management Unit accept and recommended by Infrastructure Planning and development Directorate in consultation with end user department, for sign -off. Design Development Report (i) The Design Development Report must, as necessary: a) Develop, in detail, the approved concept to finalise the design and definition criteria. b) Establish the detailed form, character, function and costing. c) Define the overall size, typical detail, performance and outline specification for all components. d) Describe how infrastructure, or elements or components thereof, are to function; and how they are to be safely constructed, be commissioned and be maintained. e) Confirm that the project scope can be completed within the budget, or propose a revision to the budget. Stage 3 is complete when the Design Development Report is approved. |  |
| 4 | Design documentation | 6A Production information | Project management Unit accept and recommended by Infrastructure Planning and development Directorate in consultation with end user department, for sign -off. |
|  |  | 6B Manufacture, fabrication and construction information | Project management Unit accept and recommended by Infrastructure Planning and development Directorate in consultation with end user department, for sign -off Design Documentation (i) Design documentation provides: a) the production information that details performance definition, specification, sizing and positioning of all systems and components that will enable construction; b) the manufacture, fabrication and construction information for specific components of the work, informed by the production information. Stage 4 is complete when the Design Documentation Report is approved. |
| 5 | Works | The contract manager certifies completion of the works or the delivery of goods and associated services Submitted to PMU accepts, and The Director of IPD responsible for implementation for the Infrastructure Service sign -off on completion of the works or the delivery of goods and associated services for projects. Completed Works capable of being used or occupied (i) Completion of the Works Stage requires: a) Certification of the completion of the works in accordance with the provisions of the contract; or b) Certification of the delivery of the goods and associated services in accordance with the provisions of the contract. Stage 5 is complete when the Works Completion Report is approved. |  |
| 8 | Handover | The Director of the User Department the owner or end user accepts liability for the works. Works which have been taken over by the user or owner; Completed Training; Record Information (i) The handover stage requires the following activities to be undertaken: a) Finalise and assemble record information which accurately reflects the infrastructure that is acquired, rehabilitated, refurbished or maintained; b) Hand over the works and record information to the user organisation and, if necessary, train end user staff in the operation of the works. Stage 6 is complete when the Handover/Record Information Report is approved. |  |
| 9 | Close-Out | Defects Certificate or Certificate of Final Completion; Final Account; Close-Out Report The contract manager or certifies the defects certificate in accordance with the provisions of the contract and Submitted to PMU to accepts the defects certificate. The Director of IPD responsible for implementation for the Infrastructure Service sign -off The contract manager certifies final completion in accordance with the provisions of the contract and handover all record information to PMU PMU accept all record information Director IPD accepts the close out report and approved final payment certificate. The Close-Out Stage commences when the end user accepts liability for the works. It is complete when: a) Record information is archived; b) Defects certificates and certificates of final completion are issued in terms of the contract; c) Final amount due to the contractor is certified in terms of the contract; d) Close-Out Report is prepared by the Implementer and approved by the Municipality. Stage 7 is complete when the Close-out Report is approved. |  |

Table 2: 	Responsibilities for approving or accepting end of stage deliverables in the control framework for the management of infrastructure delivery

# Gateway Reviews

## Gateway reviews for mega capital projects

- The MFMA (Act 56 of 2003), section 19 (2) states: “Before approving a capital project in terms of subsection (1)(b), the council of a municipality must consider the projected cost covering all financial years from the start until the project is operational; and the future operational costs and revenue on the project, including municipal tax and tariff implications.”

- The LGFIDPM prescribes the Gateway Review at the end of stage 2, as the minimum requirement to comply with section (i) above.

- The focus of such a review must be on the quality of the documentation in the first instance, and thereafter on:

- Deliverability: the extent to which a project is deemed likely to deliver;

- Expected benefits: within the declared cost, time and performance area;

- Affordability: the extent to which the project’s level of expenditure and financial risk can be accepted, given the organization’s overall financial position, both singly, and when considering its other current and projected commitments; and

- d) Value for money: The optimum combination of whole life costs and quality (or fitness of purpose), to meet the user’s requirements.

- For the purpose of this policy , the minimum threshold for mega projects at Elundini Municipality is R50 000 000 and above

## Establishment and composition  of gateway review team

- The accounting Officer shall appoint members of the gateway review on all project above R50 Million.

- A gateway review team must comprise of not less than three persons who are neither involved, nor associated with the project, but have a broad understanding of the subject matter.

- A gateway review must be led by a person who has experience in the planning of infrastructure projects and is registered as a professional with a statutory council under the built environment professions.

- The members of the team must, as relevant, have expertise in the key technical areas, cost estimating, scheduling and implementation of similar projects.

## Terms of reference for the gateway team

- The gateway review team must base its findings primarily on:

- The information contained in the end-of-stage deliverable;

- Supplementary documentation, if any, provided by key staff and obtained during an interview process; and

- Interviews with key staff members and stakeholders.

- The gateway review team must issue a report at the conclusion of a gateway review, which reflects the team’s assessment of the information at the end of a stage; and provides findings or recommendations on areas where further work should be undertaken to improve such information.

- The gateway review findings must be classified by the gateway review team as:

- Critical: Findings that pose adverse effect to the project or package. Critical findings are findings related to the stage deliverable that are wholly unacceptable.

- Major: Findings that pose a potentially adverse effect to the project or package. Major findings are serious findings and are in direct violation of key legislation, e.g. The Constitution of the Republic of South Africa, the MFMA or the PPPFA.

- Minor: Findings that do not pose any adverse effect to the project or package. Minor findings indicate the need for improvement of practices and processes.

- A Stage 2 deliverable must not be approved until such time that all findings have been resolved

# Supervision of this Infrastructure Procurement and Delivery Policy

The SCM shall be directly supervised by the CFO in consultation with the Directorate Infrastructure Planning and Development (IPD) or delegated official in terms of section 82 of the MFMA.

## 8.1.1.Objections and complaints

### 8..1.1.1 Objections and complaints are dealt with in section 102 of the Master SCM policy

## 8.1.2 Resolution of disputes, objections, complaints and queries

8.1.2.1 	Resolution of disputes, objections, complaints and queries are dealt with in accordance with section 102 of the Master SCM policy

8.1.2.2     The municipal manager shall appoint an independent and impartial person, not directly involved in the infrastructure delivery management processes to assist in the resolution of disputes between the municipality any decisions or actions taken in the implementation of the supply chain management system;

- any matter arising from a contract awarded within the Elundini Local Municipality infrastructure delivery management system; or

- to deal with objections, complaints or queries regarding any such decisions or actions or any matters arising from such contract.

#### 8.1.2.3    The municipal manager shall assist the person appointed in terms of 8.1.2.1 to perform his or her functions effectively.

8.1.2.4.     The person appointed in terms of 8.1.2.1 shall:

- strive to resolve promptly all disputes, objections, complaints or queries received; and

- submit monthly reports to the municipal manager on all disputes, objections, complaints or queries received, attended to or resolved.

8.1.2.5       A dispute, objection, complaint or query may be referred to the Eastern Cape Provincial    Treasury if:

a)	the dispute, objection, complaint or query is not resolved within 60 days; or

b)	no response is forthcoming within 60 days.

8.1.2.6 If the Eastern Cape Provincial Treasury does not or cannot resolve the matter, the dispute, objection, complaint or query may be referred to the National Treasury for resolution.

# Control framework for infrastructure delivery management

.

## 9.1 Assignment of responsibilities for approving or accepting end of stage deliverables

The responsibilities for approving or accepting end of stage deliverables shall be as stated in Table 2. The legend on the tables indicate the responsibilities between the Client, Implementing Agent

## 9.2 	Additional requirements

The following additional requirements apply:

- Directorate Infrastructure Planning and Development (IPD shall play an important role in determining the risk management and internal control to mitigate the risks;

- the Directorate Infrastructure Planning and Development (IPD) shall be the implementing agent of choice for all projects; and

- in cases where Directorate Infrastructure Planning and Development (IPD)does not have capacity to implement, Directorate Infrastructure Planning and Development (IPD)may engage sub-IAs or delivery agents after consultation with the relevant client department, user departments, Municipal Treasury and Strategic User Department.

# Committee system for procurement

  - A committee system comprising the Bid Specification, Evaluation and Adjudication Committee shall be applied to all procurement procedures in line with the Master SCM policy .

# Framework Agreements

## 11.1 The rationale of Framework Agreement and Fundamental Principles.

- A framework agreement, in the context of this policy is an agreement between the municipality and one or more supplier / service provider, the purpose of which is to establish the terms governing orders to be awarded during a given period, in particular with regard to price and where appropriate, the quantity envisaged.

- Framework Agreements also enable the municipality to procure goods / works / services including engineering or construction goods /works and/or services on an instructed basis, over a term without any commitment to the quantity of the goods / works / services instructed, in the absence of a fully developed scope of work.

- When the contract for the framework agreement is concluded, it does not have a Rand value or specific volumes of goods / works / services.

- The Municipality enters into contractual obligations with a Rand value when it places task / supply orders against the framework agreement. The Organ of State can place orders against the framework agreement from the date of commencement of the agreement up to the date of termination or end date of contract. It must be borne in mind that contracts awarded during the currency of the agreement may extend beyond the termination date of the agreement. In such instances, the goods / works / services must be executed in terms of the conditions of the agreement until its logical conclusion. Thus, the terms and conditions of the agreement remain valid and binding on all parties to the agreement until the task / supply has been successfully completed / delivered and signed-off.

- Orders are placed without going through a procurement process (the procurement process has already taken place for the arrangement of the framework agreement). However, with some infrastructure works, the scope / full scope of work is not known at the time of arranging the framework agreement. In such instances, a limited bidding process will be followed amongst the approved suppliers / service providers on the framework agreement through a quotations process to appoint the contractor for the specific goods / works / services.

- When a framework agreement is concluded, it has a zero value or specified volumes of goods / works / services. This means that the client has no obligation to pay the suppliers / service providers appointed to the framework agreement. Such an obligation only arises when the client places an order with the suppliers / service providers against the framework agreement.

- The Municipality has the prerogative as to how many orders are to be issued against the framework agreement and when to issue such orders. The Municipality might decide not to issue orders against the framework agreement during the course of the agreement or might decide to issue a large number of orders against the framework agreement. This is completely at the discretion of the municipality and based on need and availability of budgeted funds. However, when an order is issued against a framework agreement, it must be implemented in line with the terms and conditions in the framework agreement as well as the relevant contract / service level agreement (JBCC, GCC, FIDIC, NEC in the case of infrastructure related requirements which are also referred to as the form of contract).

- The Municipality may decide to enter into Framework agreements under the following conditions:

- The goods / works / services are of a repetitive nature and that are the same or similar in nature;

- The precise quantity of goods / works / services is not yet known;

- Whilst the goods / works / services are to some extent standardised, there may be some site-specific (i.e. a fully developed scope of work is not yet available), transport and logistical, variables which may not yet be known; and

- A framework agreement can be arranged for either a single procuring entity or for multiple entities which require the same or similar goods / works / services

- Framework agreements reduce the employer’s need to re-advertise and approach the market for goods, services or works falling within the scope of the agreement over the term of the agreement and the number of relationships to be managed. They also provide employers with programming flexibility to manage expenditure relating to the delivery and maintenance of infrastructure over time, and enable collaborative relationships to develop in order to deliver better value and project outcomes, particularly those relating to contractor development, community participation and skills development.

- Framework contracts need to contain terms which establish:

- the rights and obligations of the contracting parties, and the agreed procedures for the administration of the contract and the issuing of orders;

- the term of the agreement during which an order may be issued;

- the scope of work which may be included in an order to enable decisions to be made as to what is covered in the agreement and what needs to be procured outside of the agreement;

- the basis by which contractors will be remunerated for work performed in terms of an order, if and when such an order is issued; and

- where a framework contract is entered into with more than one contractor, the manner in which competition amongst framework contractors for a package order is to be conducted.

- Framework agreements that are entered into may not commit the municipality to any quantum of work beyond the first batch, task or package order. Furthermore, such agreements may not bind the municipality to make use of such agreements to meet needs. The market needs to be approached for goods, services and works whenever better value in terms of time, cost and quality may be obtained.

- The term of a framework agreement may not exceed the period stated in the employer’s procurement policy which generally does not exceed 3 years except approved in terms of Section 33 of the MFMA

.

- Task or Package Orders:

  - may only cover goods, services and work falling within the scope of work associated with the agreement which may not be amended for the duration of the contract;

  - may not be issued after the expiry of the term of the framework agreement, see the table below :

  - Contractors may not proceed with work associated with a batch, task or work package until such time that an order has been issued in terms of the contract.

## 11.2 Invitation of Bids for Framework Contracts (PG5)

- The invitation of potential suppliers / service providers must be in compliance with the prescribed requirements and advertised as widely as possible as per the Elundini SCM Policy and Procurement Gate 5 taking into consideration all the gates from PG 1 to PG 4.

## 11.3 Evaluation, Adjudication and Appointment of Suppliers / Service Providers (PG6)

- The ELM Committee system applies

- The evaluation of bids must follow the normal evaluation processes in line with Procurement Gate 6 (PG6)

- The recommendation of the bid evaluation committee will be for the appointment of suppliers / service providers to the framework agreement and not for actual allocation of work / issuing of orders

## 11.4 Awarding of Contracts (PG7) .

- Awards must be in line with the requirements of Procurement Gate 7.

- Upon approval of the recommendations of the bid adjudication / transversal bid adjudication committee by the Accounting Officer, the municipality must issue letters of appointment to the qualifying bidders. The letters of appointment must clearly indicate that the relevant bidder has been appointed to the framework agreement and that goods / works / services must only be delivered / performed upon receipt of an official order. The letters of appointment must also include other operational details of how the framework agreement will function including:

- that such letter does not automatically guarantee any quantity or value of supplies / works;

- acceptance of appointment to the framework agreement;

- signing of the agreement (non-committal service level agreement if required in addition to the framework agreement), etc.; and

- Each appointed supplier / service provider must be issued with a copy of the framework agreement

- Procedure of selection for orders.

## 11.5 Contract Management / Monitoring and Close-Out (PG8).

- Constant monitoring and active management of contracts are essential to ensure that all obligations are fulfilled and that the contract proceeds with as little disruptions as possible.

- The monitoring and management of contracts must be undertaken in accordance with the principles and requirements stipulated in the Elundini Municipality Contract Management Policy as they relate to managing contractor performance, price adjustments, variations, disputes, etc.

- A key consideration in entering into a framework agreement is to decide on how contractors are to be paid for broadly defined work which is usually not sufficiently scoped to enable it to be priced at the time when the agreement is entered into. Price lists with a transparent methodology to determine the price of items that are not included in the price list at the time of tender may be used where work in orders is largely repetitive in nature.

- Cost based pricing strategies are required where there is little or no repetition in the work required in successive orders. It should be noted that the FIDIC, JBCC and SAICE forms of contract for works do not make provision for cost based pricing strategies and don’t provide a transparent means for determining the price of items that are not included in the price list at the time of tender.

- The NEC3 family of contracts addresses both these requirements and more. The NEC3 family of contracts facilitates the implementation of sound project management principles and practices as well as defining legal relationships. It is drafted on a relational contracting basis based on the belief that collaboration and teamwork across the whole supply chain optimises the likely project outcomes and is therefore based on “discussion at the time” rather than “argument later.” It contains clear procedures with defined time limits for actions to be taken and provides for effective control of change, speedy agreement of time, quality and cost impacts of change, improved forecasting of end costs and end dates. It also includes requirements for the parties to issue to each other early warnings of risks relating to time, cost and quality. It assesses compensation events (events for which the employer is at risk) which entitle the contractor to more money on the basis of cost as defined in terms of the contract uplifted by any percentages for overheads and profit or fees provided for in the contract for work already done or a forecast for the work not yet done.

- The municipality without confining the system to the NEC Form of contract deems it fit that the NEC3 family of contracts is accordingly well suited to form the basis of framework agreement and whenever necessary pursue other forms of contract.

## 11.6. Issuing of  Task Orders

- In the case of a framework agreement wherein all the terms and conditions are not clearly defined or the scope of work is not fully developed at the time of arranging the framework agreement, e.g. in engineering and construction related works, then the qualifying bidders are required to compete for the specific goods / works / services when such are required through a limited or closed bidding process.

- Where competition takes place amongst framework contractors, it needs to be conducted in a non-discriminatory manner such that competition is not distorted.

- The opening of competition amongst framework contractors is only necessary when no justifiable reasons for not doing so cannot be found.

- This process could take the form of quotations, and would usually be for the rates / work items not included in the original procurement process.

- This second stage limited bidding would also allow for adjustments to P&G items affected by the duration, location, complexity, and other relevant factors.

- The relevant evaluation criteria which are in compliance with the terms and conditions of the framework agreement must be adhered to in evaluating the responses of suppliers / service providers and making an award of contract.

- Such evaluation and adjudication must be undertaken by the standing oversight committee as appointed by the Accounting Officer.

- The successful supplier / service provider must be issued with a formal letter of award of contract but must only commence with the supply or works upon receipt of an official written task order.

- No task order will be issued where there is valid proof for poor performance during the implementation of the previous task order.  Reasons for poor performance must be justifiable and in line with the form of contract entered into between the parties.

Table 1: Procurement activities, key actions, responsibilities and gates associated with the issuing of

orders

| Activity |  |  |
| --- | --- | --- |
| 1 FG 1 | Confirm justifiable reasons for selecting a framework contractor where there is more than one framework agreement covering the same scope of work Initiate Limited bidding process | Oversight Committee |
| 2 | Prepare procurement documents | SCM |
| 3 FG 2 | Obtain approval for procurement documents | A/O |
| 4 FG 3 | Confirm that budgets are in place | IP&D CFO |
| 5 | Quotations amongst framework contractors not invited: Issue draft order documentation and consult with contractor and prepare evaluation report ( Supporting documents for valid reasons for not requesting quotes from other contractors) Quotations amongst framework contractors invited: Invite quotations from all framework contractors participating in the agreement, receive and evaluate submissions and prepare evaluation report | SCM |
| 6 FG 4 | Draft Task Order , Authorize the issuing of the order | IP&D SCM |
| 7 | Log order onto management system (if applicable ) | SCM |
| 8 | Issue order to contractor | SCM |
| 9 | Notify issuing of order to oversight person | SCM |
| 10 | Administer orders in accordance with contract and confirm compliance with requirements | IP&D SCM |

## 11.7 Making use of another organisation’s framework agreement

Elundini Municipality may make use of another organisation’s framework agreement provided that:

- it was put in place following a competitive tender process;

- the agreement is suitable for the intended use;

- the required goods, services and works fall within the scope of such contract;

- the framework contractor agrees to accept an order from the other organisation and such an organisation undertakes to pay the contractor in accordance with the terms and conditions of the agreement; and

- the term of the framework agreement does not expire before the issuing of the required orders.